## Cover Page
State Scholarship
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy - Project solutions
Role
Signature
| Date | 2019-11-20
Project ID: B012 |  |  |  | <SCI.ID> / Ver: V 1.0
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog State Scholarship Project ID: B012 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | User Registration | User (Student / Scholarship provider ) | As a user, I should be able to register to this website | 1. Clicking on the “Register” button should open the Registration form. 2. User to fill the basic attributes: First Name Last Name DoB Gender Contact Number Category User Id Password 3. Clicking ‘Submit’ button should validate the datatype constraints for each field 4. User failing to provide information for the mandatory fields be presented with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field validation, save the information in the database 6. Upon saving the information in the database, display the message “New user created successfully”
US_2 | User Authentication | User | As a user, I should be able to log in | 1. Clicking “Sign In” link should allow the user to enter the User ID and Password and click 2. Portal to validate the entered user credentials against the database and allow login for registered users. 3. If User ID is not present, it should throw error saying " User ID not present. For wrong password, it should say "Password not matching"
US_3 | Admin credentials | Admin | As a Admin, I should be able to log in | 1. System should have a Admin Login credentials stored in the DB. 2. When keyed in with correct credentials, it should log in. 3. If Admin ID is not present, it should throw error saying " User ID not present. For wrong password, it should say "Password not matching"
US_4 | Log off | User | As a user, I should be able to log off | 1. When the user clicks Log off, the system should disconnect from the system.
US_5 | Password reset | User | As a user I should be able to reset password | 1. During registration, System should pop up three secret questions for Password recovery. 2. When the user clicks Forgot User ID, system should ask for the secret questions. On answering the questions correctly, the User ID should be displayed. 3. When the user clicks Forgot Password, system should ask for the User ID and secret questions. On answering the questions correctly, the password reset page should be displayed. 4. On entering the details in the password reset page, password should be validated 5. On clicking Submit, the details should be saved to the Database
US_6 | Student Scholarship registration | User (Student) | As a student I should be able to register for scholarship. | 1. Student on clicking register for Scholarship should redirect to the scholarship registration page. 2. Student should be able to enter the details required like Marks, Grade, Dream course, College etc. 3. Clicking ‘Submit’ should validate the datatype constraints for each field. 4. Student failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red. 5. Post-successful field level validation, save the information in the database. 6. Upon saving the information in the database, display the message ‘Your details are submitted successfully’. 7. Clicking ‘Submit’ should validate the datatype constraints for each field.
US_7 | View Scholarship request | Scholarship provider. | As a scholarship provider, I should be able to view the request. | 1. On clicking View request it should redirect to the request Page. 2. Scholarship providersshould be able to view all the requests raised by the students. 3. Clicking each request ID, he should be able to view the details.
US_8 | Approve the request | Scholarship provider. | As a scholarship provider, I should be able to approve the request. | 1. On clicking the request ID, it should display the details. 2. He should be able to validate the details. 3. If available funds and eligibility criteria matches, he can approve. 4. Once approved the status should be updated in the DB. 5. Approved request should not be listed in the view
US_9 | Update Status | System | As a system, I should be able to update the status upon approval. | 1. When the scholarship provider approves the request, the status should be updated in theDB.
US_10 | Approved requests | Scholarship provider. | As a scholarship provider, I should be able to view the approved request. | 1. On clicking Approved request link, it should display the list of approved request. 2. On clicking the request ID, it should display the details.
US_11 | Admin Reporting | Admin | As an Admin I should be able to generate Report | 1. On clicking reports, options should be displayed. Scholarship providers (NGO) Students benefited of NGO Students awaiting scholarship 2. Report should be generated for current year. 3. User should have the option to download as PDF, export to excel. 4. User should have the option to pull previous years reports as well.
US_12 | Help | User | As a user, I should be able to get help. | 1. Page that displays the basic details text about how to search documents 2. Portal to display a form that allows user to report the technical issues through Email: Issue Description Send Button 3. Portal to display the Contact number to report issues. 4 Resolutions provided by admin should be viewable.
US_13 | Resolve help request | Admin | As an admin, I should be able to view and provide resolution for the help request. | 1. Clicking on help request should list all the requests raised by the user. 2. Clicking the request ID, it should display the details. 3 Admin should be able to provide resolution. 4 The details should be saved to the DB.

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000